## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a supervisor, I want to upload an audio call and get it transcribed automatically | M | None | Rameshwar Pawar | Done
Sprint 1 | Sprint 1 | US-02 | As a supervisor, I want speaker labels (Agent/Customer) on transcript | M | US-01 | Rameshwar Pawar | Done
Sprint 2 | Sprint 2 | US-03 | As a QA analyst, I want 10 quality metrics scored per call (1-10 + F1) | M | US-01 | Rameshwar Pawar | Done
Sprint 2 | Sprint 2 | US-04 | As a QA analyst, I want chat log (.txt) files processed like audio | M | US-03 | Rameshwar Pawar | Done
Sprint 3 | Sprint 3 | US-05 | As a manager, I want an agent performance dashboard with trend charts | M | US-03 | Rameshwar Pawar | Done
Sprint 3 | Sprint 3 | US-06 | As a manager, I want to view complete call history per agent | M | US-05 | Rameshwar Pawar | Done
Sprint 4 | Sprint 4 | US-07 | As a QA lead, I want to batch process up to 500 calls simultaneously | M | US-01 | Rameshwar Pawar | Done
Sprint 4 | Sprint 4 | US-08 | As a compliance officer, I want calls auto-checked against policy docs | S | None | Rameshwar Pawar | Done
Sprint 4 | Sprint 4 | US-09 | As an admin, I want critical issues to trigger automated alerts | S | US-03 | Rameshwar Pawar | Done
Sprint 5 | Sprint 5 | US-10 | As a user, I want a dark modern UI with 3D visual elements | S | None | Rameshwar Pawar | Done
Sprint 5 | Sprint 5 | US-11 | As a user, I want a chatbot to answer platform questions | S | None | Rameshwar Pawar | Done
Sprint 6 | Sprint 6 | US-12 | As an admin, I want to delete outdated policy documents | C | US-08 | Rameshwar Pawar | Done
Sprint 6 | Sprint 6 | US-13 | As a developer, I want comprehensive documentation (E2E, Agile, PPT) | C | None | Rameshwar Pawar | Done
Future | Future | US-14 | As a supervisor, I want real-time transcription with <10s latency | W | None | TBD | Planned
Future | Future | US-15 | As a manager, I want telephony integration with call center software | W | None | TBD | Planned
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T-001 | Set up Flask project structure and virtual environment | 17-Feb-26 | 17-Feb-26 | Rameshwar Pawar | Development | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-002 | Configure .env for API keys and load with python-dotenv | 17-Feb-26 | 17-Feb-26 | Rameshwar Pawar | Development | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-003 | Create POST /api/upload endpoint with multipart form handling | 18-Feb-26 | 18-Feb-26 | Rameshwar Pawar | Development | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-004 | Deepgram SDK integration with nova-2 model | 18-Feb-26 | 19-Feb-26 | Rameshwar Pawar | Development | Done | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-005 | Speaker diarization — first-to-speak=agent heuristic | 19-Feb-26 | 19-Feb-26 | Rameshwar Pawar | Development | Done | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-006 | Transcript formatter with MM:SS timestamps | 20-Feb-26 | 20-Feb-26 | Rameshwar Pawar | Development | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-007 | OpenRouter API integration — Claude 3 Haiku | 22-Feb-26 | 22-Feb-26 | Rameshwar Pawar | Development | Done | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-008 | 10-metric LLM prompt engineering and JSON parser | 22-Feb-26 | 23-Feb-26 | Rameshwar Pawar | Development | Done | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-009 | F1 score calculation from precision/recall metrics | 24-Feb-26 | 24-Feb-26 | Rameshwar Pawar | Development | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-010 | Chat log (.txt) processor — speaker mapping logic | 25-Feb-26 | 25-Feb-26 | Rameshwar Pawar | Development | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
US-05 | T-011 | Chart.js integration — radar, bar, F1 gauge charts | 27-Feb-26 | 28-Feb-26 | Rameshwar Pawar | Development | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
US-05 | T-012 | Agent cards UI with avg score, calls, alerts | 01-Mar-26 | 01-Mar-26 | Rameshwar Pawar | Development | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-06 | T-013 | Agent detail page — score trend chart and call history | 03-Mar-26 | 03-Mar-26 | Rameshwar Pawar | Development | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
US-07 | T-014 | Async job queue for large file batch processing | 05-Mar-26 | 06-Mar-26 | Rameshwar Pawar | Development | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
US-08 | T-015 | Policy RAG engine — TF-IDF indexing and semantic search | 06-Mar-26 | 07-Mar-26 | Rameshwar Pawar | Development | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
US-09 | T-016 | Alert engine — 6 alert types with severity levels | 08-Mar-26 | 10-Mar-26 | Rameshwar Pawar | Development | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Feb 17 | None | Project initialized, Flask + Deepgram SDK installed
Sprint 1 | Feb 18 | Deepgram empty utterances for short files | Used word-level fallback for transcription
Sprint 1 | Feb 19 | None | Speaker diarization working
Sprint 1 | Feb 20 | None | Transcript formatter complete
Sprint 1 | Feb 21 | None | Sprint 1 review complete
Sprint 2 | Feb 22 | LLM JSON parsing issues | Added robust multi-format response parser
Sprint 2 | Feb 24 | None | 10 metrics scoring pipeline complete
Sprint 2 | Feb 25 | None | Chat log processor implemented
Sprint 2 | Feb 26 | None | Sprint 2 complete — full scoring pipeline working
Sprint 3 | Feb 27 | Chart.js mobile sizing | Fixed with responsive:true option
Sprint 3 | Mar 01 | None | Agent dashboard complete
Sprint 3 | Mar 03 | None | Agent detail page complete
Sprint 3 | Mar 04 | None | Sprint 3 review complete
Sprint 4 | Mar 05 | Thread safety for concurrent batch jobs | Used threading.Lock for shared state
Sprint 4 | Mar 06 | None | Batch processing working — 50 files tested
Sprint 4 | Mar 08 | None | Policy compliance checking integrated
Sprint 4 | Mar 10 | Supabase password special chars | Used URL encoding for connection string
Sprint 4 | Mar 12 | None | Sprint 4 review complete
Sprint 5 | Mar 13 | backdrop-filter on old Safari | Added -webkit-backdrop-filter prefix
Sprint 5 | Mar 17 | None | 3D canvas animation complete
Sprint 5 | Mar 18 | OpenRouter rate limits on free tier | Added retry with exponential backoff
Sprint 5 | Mar 20 | None | Sprint 5 review complete
Sprint 6 | Mar 21 | None | Duplicate navbar bug identified and fixed
Sprint 6 | Mar 22 | None | Transcription improvement deployed
Sprint 6 | Mar 23 | None | agentAlertsList null bug fixed
Sprint 6 | Mar 24 | None | Policy delete feature complete
Sprint 6 | Mar 25 | None | All documentation created
Sprint 6 | Mar 26 | None | Project delivered and deployed to Vercel

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 17-Feb-26 | 21-Feb-26 | Rameshwar Pawar | Better error logging from the start | Testing without structured test cases | Daily written standup logs | Adopted structured test cases from Sprint 2
2 | Sprint 2 | 22-Feb-26 | 26-Feb-26 | Rameshwar Pawar | LLM prompt versioning | Hardcoding model names in code | Incremental commits for each feature | Moved all model names to env vars
3 | Sprint 3 | 27-Feb-26 | 04-Mar-26 | Rameshwar Pawar | Mobile-first CSS development | Chart sizing hacks | Testing on Chrome + Firefox | Used proper Chart.js responsive options
4 | Sprint 4 | 05-Mar-26 | 12-Mar-26 | Rameshwar Pawar | DB schema versioning/migrations | Synchronous processing for large files | Keeping UI and API changes separate | Added async job queue with polling
5 | Sprint 5 | 13-Mar-26 | 20-Mar-26 | Rameshwar Pawar | CSS variable consistency | Using !important inline overrides | Performance testing after CSS changes | Centralized all CSS variables in :root
6 | Sprint 6 | 21-Mar-26 | 26-Mar-26 | Rameshwar Pawar | Writing docs alongside code | Leaving bug fixes to last sprint | Checking Vercel logs after deploy | Applied lessons to future planning
7